## sheet1
Test Case ID | Bug ID | Test Summary | Test Steps | Test Data | SQL Query | Expected Result | Actual Result | Sevirty | Priority
TC-DB-09 | BUG-DB-01 | Verfiy NO new orders with shipped date | Run the query to find orders WHERE status_id = 0 AND shipped_date IS NOT NULL | Table: orders Columns: status_id, shipped_date | SELECT * FROM northwind.orders WHERE status_id = 0 AND shipped_date IS NOT NULL; | No records should be returned (Result set is empty) | Result set is NOT empty | Critical | High
TC-DB-10 | BUG-DB-02 | Verify NO new orders with payment date | Run the query to find orders WHERE status_id = 0 AND paid_date IS NOT NULL | Table: orders Columns: status_id, paid_date | SELECT * FROM northwind.orders WHERE status_id = 0 AND paid_date IS NOT NULL; | No records should be returned (Result set is empty) | Result set is NOT empty | Critical | High
TC-DB-15 | BUG-DB-03 | Verify NO orders without tax status id | Run the query to find orders WHERE tax_status_id IS NULL | Table: orders Columns: tax_status_id | SELECT * FROM northwind.orders WHERE tax_status_id IS NULL; | No records should be returned (Result set is empty) | Result set is NOT empty | Critical | High
TC-DB-16 | BUG-DB-04 | Verfiy NO shipped or complete orders without shipping fee | Run the query to find orders WHERE status_id = 2 OR 3 AND shipping_fee = 0 | Table: orders Columns: status_id, shipping_fee | SELECT * FROM northwind.orders WHERE status_id IN (2,3) AND shipping_fee = 0; | No records should be returned (Result set is empty) | Result set is NOT empty | Critical | High
TC-DB-17 | BUG-DB-05 | Verify NO shippers without email address | Run the query to find shippers WHERE email_address IS NULL | Table: shippers Columns: email_address | SELECT * FROM northwind.shippers WHERE email_address IS NULL; | No records should be returned (Result set is empty) | Result set is NOT empty | Medium | High
TC-DB-18 | BUG-DB-06 | Verify NO shippers without business phone | Run the query to find shippers WHERE business_phone IS NULL | Table: shippers Columns: business_phone | SELECT * FROM northwind.shippers WHERE business_phone IS NULL; | No records should be returned (Result set is empty) | Result set is NOT empty | Medium | High
TC-DB-25 | BUG-DB-07 | Invalid status_id in order_details has no matching record in order_details_status | Run query to find order_details rows where status_id has no match in order_details_status | Table: order_details, order_details_status Columns: order_details.status_id, order_details_status.id | SELECT od.id, od.status_id FROM northwind.order_details od LEFT JOIN northwind.order_details_status ods ON od.status_id = ods.id WHERE ods.id IS NULL; | No records returned (result set is empty) | 1 record returned: order_details.id=90 has status_id=5, which does not exist in order_details_status (valid values: 0, 1, 2) | Critical | High
TC-DB-28 | BUG-DB-08 | Quantity equals 0 in order_details which violates minimum value rule | Run query to find order_details rows where quantity is 0 or less | Table: order_details Column: quantity | SELECT id, order_id, product_id, quantity FROM northwind.order_details WHERE quantity <= 0; | No records returned (result set is empty) | 2 records returned: id=90 (product_id=81) and id=91 (product_id=56) both have quantity=0 | Critical | High
TC-DB-33 | BUG-DB-09 | Multiple products have NULL minimum_reorder_quantity which is a required field | Run query to find products where minimum_reorder_quantity is NULL | Table: products Column: minimum_reorder_quantity | SELECT id, product_name, minimum_reorder_quantity FROM northwind.products WHERE minimum_reorder_quantity IS NULL; | No records returned (result set is empty) | Multiple records returned: products id 87, 88, 89, 90, 91, 92, 93, 94, 95, 96, 97, 98, 99 all have NULL minimum_reorder_quantity | Medium | Medium
TC-DB-36 | BUG-DB-10 | Some products have NULL quantity_per_unit which is required for order fulfillment | Run query to find products where quantity_per_unit is NULL | Table: products Column: quantity_per_unit | SELECT id, product_name, quantity_per_unit FROM northwind.products WHERE quantity_per_unit IS NULL; | No records returned (result set is empty) | 5 records returned: Granola (id=82), Potato Chips (id=83), Hot Cereal (id=97), Vegetable Soup (id=98), Chicken Soup (id=99) all have NULL quantity_per_unit | Medium | Medium
TC-DB-49 | BUG-DB-11 | Verify Product Categories | 1. Join products with categories. 2. Check names. | categories table | SELECT p.product_name, c.category_name FROM products p JOIN categories c ON p.id = c.id; | Each product has a valid category name. | Doesn't match SQL result. | High | High
TC-DB-55 | BUG-DB-12 | Validate Order Quantity | 1. Check for quantities > 0. | quantity column | SELECT * FROM order_details WHERE quantity <= 0; | No records with zero or negative quantity. | Records returned. | High | High
TC-DB-57 | BUG-DB-13 | Verify order payment matches sum of details | Run query to find mismatched totals | Tables: purchase_orders, purchase_order_details | SELECT po.id FROM purchase_orders po JOIN purchase_order_details pod ON po.id = pod.purchase_order_id GROUP BY po.id, po.payment_amount HAVING po.payment_amount <> SUM(pod.quantity * pod.unit_cost); | No records should be returned | Result set is not empty (28 rows returned) | High | High
TC-DB-60 | BUG-DB-14 | Verify NO invoices linked to non-existent order | Run query to find invalid order_id | Tables: invoices, purchase_orders | SELECT i.id FROM invoices i LEFT JOIN purchase_orders po ON i.order_id = po.id WHERE po.id IS NULL; | No records should be returned | 35 rows returned (Found invoices with non-existent order_id) | critical | High
TC-DB-70 | BUG-DB-15 | Verify system enforces NOT NULL constraints | Run INSERT query leaving mandatory field NULL | Table: purchase_order_status Column: status | INSERT INTO purchase_order_status (id, status) VALUES (99, NULL); | Database throws 'Column cannot be null' error | The record was inserted successfully (Constraint is missing) | medium | High
TC-DB-71 | BUG-DB-16 | Verify system prevents deleting referenced parent row | Run DELETE query on an order that has details | Table: purchase_orders Column: id | DELETE FROM purchase_orders WHERE id = 1; | Database throws 'Cannot delete or update a parent row' error | The record was deleted successfully (1 row affected). Missing Foreign Key Constraint | critical | High
TC-DB-74 | BUG-DB-17 | Verify altering a paid order's amount is restricted | Run UPDATE query to change amount on paid order | Table: purchase_orders Column: payment_amount | UPDATE purchase_orders SET payment_amount = 9999 WHERE payment_date IS NOT NULL AND id = 1; | Triggers block update OR logic fails validation | The update was successful. System allowed modifying the amount of an already paid order. | critical | High
TC-DB-83 | BUG-DB-18 | Verify NO Orphan Sales (Sale type with NULL Customer Order) | Run the query to find sales without customer_order_id | Table: inventory_transactions Columns: transaction_type, customer_order_id | SELECT 'Orphan Sale' AS Bug_Type, id, transaction_type, customer_order_id FROM northwind.inventory_transactions WHERE transaction_type = 2 AND customer_order_id IS NULL; | No records should be returned (Result set is empty) | 49 rows found | High | High
TC-DB-84 | BUG-DB-19 | Verify NO Orphan Purchases (Purchase type with NULL PO) | Run the query to find purchases without purchase_order_id | Table: inventory_transactions Columns: transaction_type, purchase_order_id | SELECT 'Orphan Purchase' AS Bug_Type, id, transaction_type, purchase_order_id FROM northwind.inventory_transactions WHERE transaction_type = 1 AND purchase_order_id IS NULL; | No records should be returned (Result set is empty) | 43 rows found | High | High
TC-DB-87 | BUG-DB-20 | Verify presence of contact info (Email/Phone) | Run query to find missing email or phone | Table: suppliers Columns: email, phone | SELECT * FROM northwind.suppliers WHERE email_address IS NULL OR business_phone IS NULL OR email_address = '' OR business_phone = ''; | No records should be returned | 10 records found with missing contact info | High | High
TC-DB-88 | BUG-DB-21 | Verify location data (City/Country) | Run query to find missing city or country | Table: suppliers Columns: city, country | SELECT * FROM northwind.suppliers WHERE city IS NULL OR country_region IS NULL OR city = '' OR country_region = ''; | No records should be returned | 10 records found with missing location data | High | Medium
TC-DB-95 | BUG-DB-22 | Verify transaction type usage | Check if all types are used in transactions table | Tables: inventory_transaction_types, inventory_transactions | SELECT * FROM northwind.inventory_transaction_types WHERE id NOT IN (SELECT DISTINCT transaction_type FROM northwind.inventory_transactions); | All types should be linked to at least one transaction | 1 unused transaction type found | Low | Low